## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a developer, I want the system architecture, agent responsibilities, orchestration flow, and data models designed up front, so the rest of the platform has a clear contract to build against. | MUST HAVE | none | Ravi Raj Singh | 3- Completed
Sprint 1 | Sprint 1 | US-02 | As a developer, I want to paste code directly or upload a Python/Java source file, so the platform can validate its syntax before any deeper review runs. | MUST HAVE | US-01 | Ravi Raj Singh | 3- Completed
Sprint 1 | Sprint 1 | US-03 | As a developer, I want submitted code validated for syntax errors immediately, with the exact line and message shown, so I know right away if something won't even parse. | MUST HAVE | US-02 | Ravi Raj Singh | 3- Completed
Sprint 1 | Sprint 1 | US-04 | As a developer, I want OWASP guidelines and secure coding standards indexed into a RAG knowledge base (chunked, embedded, searchable), so later agents can ground their findings in real guidance. | MUST HAVE | US-01 | Ravi Raj Singh | 3- Completed
Sprint 1 | Sprint 1 | US-05 | As a developer, I want to search the secure coding knowledge base directly by topic, so I can learn why a pattern is risky, not just be told to fix it. | SHOULD HAVE | US-04 | Ravi Raj Singh | 3- Completed
Sprint 2 | Sprint 2 | US-06 | As a developer, I want a Code Analysis Agent that detects code smells, long methods, deep nesting, god classes, and other design anti-patterns in Python and Java, so quality issues surface automatically. | MUST HAVE | US-02 | Ravi Raj Singh | 3- Completed
Sprint 2 | Sprint 2 | US-07 | As a developer, I want a Security Vulnerability Agent that scans for OWASP-standard issues (SQL injection, XSS, hardcoded secrets, weak hashing, CSRF, broken access control) with severity and location, so I know exactly what to fix and where. | MUST HAVE | US-02 | Ravi Raj Singh | 3- Completed
Sprint 2 | Sprint 2 | US-08 | As a developer, I want the Code Analysis and Security Vulnerability agents to run in parallel with results merged into one findings list, so review is fast and I see everything in one place. | MUST HAVE | US-06, US-07 | Ravi Raj Singh | 3- Completed
Sprint 2 | Sprint 2 | US-09 | As a developer, I want findings validated against sample codebases with known issues and known-clean code, so I can trust the detection isn't just noise or guesswork. | MUST HAVE | US-08 | Ravi Raj Singh | 3- Completed
Sprint 2 | Sprint 2 | US-10 | As a developer, I want a clean, severity-color-coded findings panel in the UI, so critical issues are visually obvious at a glance. | SHOULD HAVE | US-08 | Ravi Raj Singh | 3- Completed
Sprint 2 | Sprint 2 | US-11 | As a developer, I want an optional 'Run code & see output' feature, so I can confirm what a snippet actually does, not just whether it parses. | COULD HAVE | US-02 | Ravi Raj Singh | 3- Completed
Sprint 2 | Sprint 2 | US-12 | As a developer, I want to export the current findings and severity summary as a downloadable PDF, so I can share a review with someone not using the app directly. | COULD HAVE | US-08 | Ravi Raj Singh | 3- Completed
Sprint 2 | Sprint 2 | US-13 | As a developer, I want a light/dark/system theme toggle, so the interface is comfortable regardless of my environment. | COULD HAVE | none | Ravi Raj Singh | 3- Completed
Planned | Planned | US-14 | As a developer, I want a Remediation Agent that suggests specific fixes and corrected code for each finding, grounded in the knowledge base. | MUST HAVE | US-07, US-09 | Ravi Raj Singh | 1- Not Started
Planned | Planned | US-15 | As a developer, I want a PR Summary Agent that rolls up all findings into a human-readable review summary I can paste into a pull request. | MUST HAVE | US-14 | Ravi Raj Singh | 1- Not Started
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 131 | 8 | 13 | 14 | 10 | 10 | 11 | 10 | 12 | 9 | 14 | 8 | 5 | 5 | 2
SPRINT 1 BACKLOG
US-01 | T-01 | Research OWASP vulnerability standards, secure coding guidelines, code smell patterns, and RAG architecture. | 2026-07-01 | 2026-07-02 | Ravi Raj Singh | Documentation | 3- Completed | 6 | Day 1: 4; Day 2: 2
US-01 | T-02 | Design system architecture, agent responsibilities, orchestration flow, and data models. | 2026-07-02 | 2026-07-03 | Ravi Raj Singh | Design | 3- Completed | 8 | Day 2: 4; Day 3: 4
US-02 | T-03 | Build FastAPI backend skeleton, config, and Pydantic data models (Submission, Finding, ReviewSummary). | 2026-07-03 | 2026-07-04 | Ravi Raj Singh | Development | 3- Completed | 6 | Day 3: 3; Day 4: 3
US-02 | T-04 | Implement Code Submission Module: paste + upload endpoints for Python/Java with syntax validation. | 2026-07-04 | 2026-07-06 | Ravi Raj Singh | Development | 3- Completed | 10 | Day 4: 3; Day 5: 4; Day 6: 3
US-02 | T-05 | Build the frontend for code submission: paste/upload tabs, language switch, code editor, validation results. | 2026-07-06 | 2026-07-08 | Ravi Raj Singh | Development | 3- Completed | 9 | Day 6: 3; Day 7: 3; Day 8: 3
US-04 | T-06 | Write secure coding knowledge base source docs (OWASP Top 10, secure coding practices, code smells) and build the chunk/embed/index pipeline. | 2026-07-08 | 2026-07-10 | Ravi Raj Singh | Development | 3- Completed | 9 | Day 8: 3; Day 9: 3; Day 10: 3
US-04 | T-07 | Index the knowledge base into the vector store and verify retrieval accuracy. | 2026-07-10 | 2026-07-11 | Ravi Raj Singh | Testing | 3- Completed | 5 | Day 10: 2; Day 11: 3
US-05 | T-08 | Build knowledge base search UI panel with category filters. | 2026-07-11 | 2026-07-12 | Ravi Raj Singh | Development | 3- Completed | 5 | Day 11: 2; Day 12: 3
US-03 | T-09 | Write and run unit tests for the syntax validator and submission API. | 2026-07-12 | 2026-07-13 | Ravi Raj Singh | Unit Test | 3- Completed | 5 | Day 12: 2; Day 13: 3
US-01 | T-10 | Write Milestone 1 architecture, agent-design, and data-model documentation. | 2026-07-13 | 2026-07-14 | Ravi Raj Singh | Documentation | 3- Completed | 4 | Day 13: 2; Day 14: 2
SPRINT 2 BACKLOG
US-06 | T-11 | Build Code Analysis Agent for Python using ast (long method, long parameter list, deep nesting, god class, mutable default argument, bare except). | 2026-07-15 | 2026-07-16 | Ravi Raj Singh | Development | 3- Completed | 8 | Day 1: 4; Day 2: 4
US-06 | T-12 | Build Code Analysis Agent for Java using structural heuristics (brace-matching, string/comment masking) mirroring the Python rule set. | 2026-07-16 | 2026-07-17 | Ravi Raj Singh | Development | 3- Completed | 7 | Day 2: 3; Day 3: 4
US-07 | T-13 | Build Security Vulnerability Agent: SQL injection and hardcoded-secret detection (Python + Java), with tainted-variable tracking across lines. | 2026-07-17 | 2026-07-19 | Ravi Raj Singh | Development | 3- Completed | 10 | Day 3: 3; Day 4: 4; Day 5: 3
US-07 | T-14 | Extend Security Vulnerability Agent: XSS, weak-hash, CSRF, and best-effort broken-access-control detection. | 2026-07-19 | 2026-07-20 | Ravi Raj Singh | Development | 3- Completed | 6 | Day 5: 3; Day 6: 3
US-08 | T-15 | Build multi-agent orchestrator: concurrent execution, merged findings, severity sort, per-agent failure isolation, knowledge-base grounding. | 2026-07-20 | 2026-07-21 | Ravi Raj Singh | Development | 3- Completed | 6 | Day 6: 2; Day 7: 4
US-09 | T-16 | Write and run detection-accuracy test suite against known-vulnerable and known-clean Python/Java fixtures. | 2026-07-21 | 2026-07-22 | Ravi Raj Singh | Unit Test | 3- Completed | 7 | Day 7: 3; Day 8: 4
US-10 | T-17 | Build the findings panel UI: severity summary chips, per-finding cards, OWASP/CWE tags, agent-error banner. | 2026-07-22 | 2026-07-23 | Ravi Raj Singh | Development | 3- Completed | 6 | Day 8: 2; Day 9: 4
US-11 | T-18 | Add optional code execution feature, PDF report export, and light/dark/system theme toggle. | 2026-07-23 | 2026-07-24 | Ravi Raj Singh | Development | 3- Completed | 8 | Day 9: 2; Day 10: 6
US-08 | T-19 | Fix config/container resilience issues found during real deployment testing (CORS auto-detection, execution auto-enable, knowledge-base auto-build on startup). | 2026-07-24 | 2026-07-25 | Ravi Raj Singh | Bug Fixing | 3- Completed | 6 | Day 10: 3; Day 11: 3
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 5 | Ran into a tricky edge case validating Java syntax without a JDK available in every environment. | Built a structural fallback validator (balanced braces/parens, class declaration check) that degrades gracefully when javac isn't installed, instead of failing outright.
Sprint 1 | Day 9 | The RAG ingestion pipeline needed to avoid duplicating knowledge base chunks every time a document was edited and re-indexed. | Made chunk IDs deterministic (doc slug + chunk index) so re-running ingestion updates existing chunks instead of creating duplicates.
Sprint 2 | Day 3 | The XSS detector was missing a common real-world pattern: HTML built on one line and rendered via a variable on a later line. | Added the same tainted-variable-tracking approach already used for SQL injection, so the detector follows a variable across lines instead of only matching same-line patterns.
Sprint 2 | Day 7 | Java code execution kept crashing silently with no useful error message. | Traced it to a 256MB memory limit that was too strict for the JVM to even start; removed that specific limit for Java, verified with a direct reproduction test.
Sprint 2 | Day 8 | After removing the memory limit, Java execution still failed, this time due to a process-count limit blocking the JVM's own garbage-collector threads. | Removed that limit for Java specifically too, and confirmed the fix by reproducing the exact failure and re-testing.
Sprint 2 | Day 9 | GitHub's push protection blocked a commit because test fixtures used realistic-looking fake API keys for testing the secret-detection rule. | Rewrote the fake keys so they no longer match real credential formats, while still testing the same detection logic.
Sprint 2 | Day 10 | The deployed environment kept losing its configuration and knowledge base index every time the container restarted, breaking the app repeatedly. | Made CORS and code-execution settings self-configuring from the container's own environment, and added an automatic startup check that rebuilds the knowledge base index if it's found empty.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-07-01 | 2026-07-14 | Ravi Raj Singh | Documenting architecture and agent contracts before writing implementation code. | Assuming a feature works without writing a fixture-based test to prove it. | Keeping detection logic and its test fixtures side by side so accuracy claims are verifiable, not just asserted. | Adopted a fixed data contract (Finding/ReviewSummary schema) early so later milestones would be additive instead of requiring rewrites.
2 | 2 | 2026-07-15 | 2026-07-25 | Ravi Raj Singh | Reproducing a bug with a minimal, real test before attempting a fix, instead of guessing at the cause. | Trusting a fix worked just because the code looked right — several real bugs (XSS tracking, Java resource limits, config resilience) were only caught by actually running the code. | Writing both a 'should detect' and a 'should NOT false-positive' test for every new detection rule. | Made backend configuration self-healing (auto-detected CORS origin, auto-enabled execution, auto-rebuilt knowledge base index) after repeated container-reset issues during deployment testing.
3
4
5
6
7