## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Ravi Raj Singh | 2026-07-11 | Java syntax validation had no fallback path for environments without a JDK installed — validation would simply be unavailable. | Sprint 1 | Ravi Raj Singh | Standards | Added a structural heuristic fallback (balanced braces, class declaration check) with a clear note when running in reduced-precision mode. | 2026-07-11 | Closed | Confirmed the fallback activates correctly when javac is unavailable.
2 | Ravi Raj Singh | 2026-07-16 | XSS detector missed the pattern where HTML is built on one line and rendered from a variable on a later line — only matched same-line HTML+sink patterns. | Sprint 2 | Ravi Raj Singh | Logical | Added tainted-variable tracking across lines (same approach as the SQL injection detector) for both Python and Java. | 2026-07-16 | Closed | Verified with a fixture test; the XSS finding now correctly appears at the render line.
3 | Ravi Raj Singh | 2026-07-16 | Java's hardcoded-secret detector flagged the same secret twice on one line — once by variable name, once by recognized key-format prefix. | Sprint 2 | Ravi Raj Singh | Logical | Added line-level deduplication and reordered priority so the more specific/certain match wins. | 2026-07-16 | Closed | Confirmed only one finding is now returned per secret, matching the Python detector's behavior.
4 | Ravi Raj Singh | 2026-07-20 | Java code execution crashed immediately with no readable error message. | Sprint 2 | Ravi Raj Singh | Logical | Root-caused to a 256MB memory limit applied to every subprocess; removed it specifically for Java, since the JVM reserves far more virtual address space just to start. | 2026-07-20 | Closed | Reproduced the exact failure directly and confirmed the fix resolves it before shipping.
5 | Ravi Raj Singh | 2026-07-21 | Java execution still failed after the memory-limit fix, this time with a garbage-collector thread creation error. | Sprint 2 | Ravi Raj Singh | Logical | Found a process-count limit was blocking the JVM's own startup threads; removed that limit for Java too. | 2026-07-21 | Closed | Verified fixed via the actual error message from a direct reproduction.
6 | Ravi Raj Singh | 2026-07-22 | GitHub blocked a push because test fixtures contained fake API keys shaped exactly like real Stripe/AWS credentials. | Sprint 2 | Ravi Raj Singh | Standards | Rewrote fake test secrets so they no longer match real credential formats, while preserving the same test coverage. | 2026-07-22 | Closed | Confirmed a clean push after a full repository-wide scan for any remaining realistic-looking secrets.
7 | Ravi Raj Singh | 2026-07-23 | Frontend still displayed 'Milestone 1' labels and locked pipeline steps after Milestone 2 features had already shipped. | Sprint 2 | Ravi Raj Singh | User Interface | Updated the hero banner, pipeline step states, and sidebar footer to reflect Milestone 2 completion. | 2026-07-23 | Closed | Verified visually and via DOM checks that all stale milestone references were updated.
8 | Ravi Raj Singh | 2026-07-23 | The knowledge base connection broke repeatedly after the development container restarted, due to a hardcoded configuration value. | Sprint 2 | Ravi Raj Singh | Maintainability | Made CORS origin and code-execution settings self-configuring, auto-detected from the container's own environment instead of a static config file. | 2026-07-23 | Closed | Confirmed the app connects correctly with no manual configuration after a fresh container restart.
9 | Ravi Raj Singh | 2026-07-23 | The knowledge base search index was empty after a container reset since it is generated data, not committed to source control. | Sprint 2 | Ravi Raj Singh | Maintainability | Added an automatic startup check that rebuilds the index if it's found empty. | 2026-07-23 | Closed | Confirmed the index rebuilds automatically on the next server start with no manual command.
10 | Ravi Raj Singh | 2026-07-23 | The PDF export feature rendered a literal '&middot;' as visible text instead of a middle-dot separator between tags. | Sprint 2 | Ravi Raj Singh | Logical | Fixed a double-escaping bug where an HTML entity was being escaped a second time; switched to a literal character instead of an entity. | 2026-07-23 | Closed | Verified by extracting and reading back the actual generated PDF text.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others